## Sheet1
RISK REGISTER
Risk ID | Asset | Threat | Vulnerability | Likelihood | Impact | Risk score/Inherent Risk | Risk level | Treatment | Control | Annex A Controls | Residual Risk | Owner | Status
R01 | Patient Database | Data breach/unauthoprized ccess | Weak authenticatiopn, no MFA for users | 4 | 5 | 20 | Critical | Mitigate | MFA for all users, RBAC, Monitoring, Strong IAM | 5.15, 5.16, 5.17, 5.33, 5.34, 8.2, 8.5, 8.10,8.11,8.12, 8.16 | 10 | IT/ Security team | Open
R02 | S3 Bucket (Medical report storage) | Public data exposure | Misconfiguration | 5 | 5 | 25 | Critical | Mitigate | Block public access, encryption, configuration monitoring | 5.15,5.23,5.34,8.3,8.12,8.16 | 10 | IT/ Security team | Open
R03 | Logging system | Undetected incidents | No centrralized SIEM | 4 | 4 | 16 | Critical | Mitigate | implement SIEM, alerts | 8.15,8.16 | 9 | Security team | Open
R04 | Production Environnment | Unauthorized changes/privilege misuse | No access review process | 4 | 3 | 12 | High | Mitigate | Quarterly access review, least privilege | 5.15,5.16,5.18,8.2,8.3,8.4 | 6 | CTO | Open
R05 | Third party services | Third party data breach | No vendor risk assessment | 3 | 4 | 12 | High | Mitigate | Vendor risk assessment, supplier aggrements | 5.19,5.20,5.21,5.22,8.30 | 6 | Compliance officer | Open
R06 | Data Backup | Data loss/ inability to recover | No restoring testing | 3 | 5 | 15 | High | Mitigate | Regular backups, backp policy, monitoring | 5.29,5.30,8.13 | 8 | DevOps | Open
R07 | End user devices | Malware | no centeralized device management | 3 | 4 | 12 | High | Mitigate | EDR, Mobile Device Management (MDM) solution | 5.11,8.1,8.7,8.8 | 6 | IT/Security team | Open
R08 | Application Layer(web/api) | Exploitation(OWASP) | No vulnerability scanning | 4 | 4 | 16 | Critical | Mitigate | Regular VAPT, secure SDLC | 8.7,8.8,8.25,8.26,8.28,8.29,8.31 | 9 | DevSecOps/security team | Open